# Construction Site Meeting Minutes

| Project |  |
| --- | --- |
| Contract reference |  |
| Meeting number |  |
| Date |  |
| Time |  |
| Location (site office) |  |
| Chair |  |
| Minutes taken by |  |
| Present (name, company, role) |  |
| Apologies |  |
| Distribution |  |

## 1. Previous minutes

[Record that the previous minutes were accepted, or list the amendments requested in writing and by whom.]

## 2. Safety

[Always first. Record facts and the status of any investigation; do not record opinions about fault.]

Incidents and near-misses since last meeting:

Toolbox talks held:

Inductions this period:

Inspections and observations:

Outstanding safety actions:

## 3. Progress against programme

[Compare with the current approved programme. Record the figures and the critical path position, not the discussion of why.]

Planned percent complete:

Actual percent complete:

Activities completed this period:

Activities planned next period:

Critical path status:

Days ahead / behind programme:

## 4. Delays and weather

[Record days lost this period and cumulatively, the cause, and any notice given under the contract.]

Days lost to weather this period / cumulative:

Other delay events and cause:

Notices given (date, clause if known):

## 5. Requests for information (RFIs)

[Open RFIs with the date raised and the date a response is due. Overdue responses are a delay record.]

RFI no.:

Subject:

Raised:

Response due:

Status:

## 6. Submittals and samples

[Every submittal in review, with its status.]

Submittal:

Submitted:

Status (approved / approved as noted / revise and resubmit / rejected):

## 7. Change orders and variations

[Each change with its cost and time effect and its approval status. A change discussed is not a change approved; record who approves and whether they have.]

CO no.:

Description:

Cost:

Time:

Status (raised / priced / approved / rejected):

## 8. Quality and inspections

Inspections held and results:

Non-conformances open:

Hold points upcoming:

## 9. Design and information

[Current drawing register revision and any information the contractor is waiting for.]

## 10. Commercial and payments

Progress claim no. and period:

Amount claimed / certified:

Retention held:

Payment due date:

## 11. Procurement and subcontractors

[Long-lead items, deliveries expected, subcontractor start dates.]

## 12. Actions and next meeting

[Number actions as meeting number dot item: 14.01, 14.02. Carry open actions forward under their original number.]

## Action items

| Action no. | Raised (meeting) | Action | By (company) | Due | Status |
| --- | --- | --- | --- | --- | --- |

## Open RFIs and submittals

| Ref. | Subject | Raised | Due | Status |
| --- | --- | --- | --- | --- |

Template from getquietnote.com/templates